## Timed Outline
Introduction to Project Management Timed Syllabus
Section | Title |  | Questions | Minutes*
1 | Introduction - Project Management |  | 1 | 6
Provide introduction to fundamental knowledge of what is involved with project management.
2-3 | Key Elements of Project Management |  | 3 | 13
Identify the common five key elements or phases of project support that project managers work in most projects.
4-7 | Project Management Areas of Competence |  | 6 | 26
List nine areas of competence the author believes will improve the chance of project success if applied by the project manager.
8 | Defining - Project Description |  | 2 | 7
Yes - a project has an industry recognized definition. You may find a project more unique than previously thought, but it can and does often include repetition.
9 | Defining - Project Location |  | 1 | 6
Discussion on the knowledge we must know about the location of our new project. Details of the project location are necessary to establish accurate planning and costing.
10 | Defining - Stakeholders |  | 1 | 6
We must know our stakeholders, meet them and learn their roles and contributions to the project. In addition, we need to recognize who the team is missing.
11 | Planning - Scope |  | 1 | 6
What is to know about scope? Everything! We will review how to acquire scope from the project documents, the owner/client, end-users and explain the importance of clearly knowing the project scope for success.
12 | Planning - Team |  | 1 | 6
Organizing the right integrated project team from different groups, directorates and even companies is critical to delivering our project on-time and within budget. This section will focus on explaining the importance of a multidisciplinary team that is essential to completing project activities.
13 | Planning - Acquisition Strategy |  | 2 | 7
The requirements of a project can exceed in-house capacity and capability to the extent the commission of support services from outside sources to provide expertise and resources is needed. To be effective in projects we must develop an acquisition strategy plan, this section provides guidelines on how to generate a strong acquisition strategy plan.
14 | Planning - Change |  | 2 | 7
Review a systematic approach to monitor for and manage changes that result in value-added versus cost overruns and schedule slips.
15 | Planning - Design |  | 2 | 8
If your project requires a design it is paramount we understand the fundamentals of a highly-structured process needed to help the owner/client and contractor/builder align on what is the final product or structure.
16 | Planning - Procure & Construct/Build |  | 2 | 7
Most projects require the purchase of services and goods that benefits from a procurement management process. This section provides step-by-step guidelines on procurements. To execute construction or build of a project it is important to recognize the type and quantity of tools, equipment and labor needed to complete the tasks. This section provides important insight on needs during the project construction/build phase.
17 | Planning - Submittals & Fabrications |  | 1 | 6
Discuss importance of submittals. Submittals often result in material approvals that if overlooked can cause cost and schedule impacts in construction. Identifying equipment or systems that require substantial fabrication versus simply ordering a product via a catalog number is critical for project success. Large equipment fabrications can be more lengthy and costly than the building they go in.
18 | Planning - Site Tests |  | 1 | 6
Review the purpose and cost benefit of factory tests. If we want a smooth startup and commissioning, we need to test our equipment and systems during the construction/build phase.
19 | Planning - Software, Kickoffs & Lessons Learned |  | 2 | 7
Discuss the details of planning, managing and leading a software project or a major activity in the project. Review what triggers warrant the need for a kickoff meeting or telecom session. Understanding lessons learned and implementing them in future projects is critical for continuous improvement. Regardless of how important we believe formally documenting lessons learned are, lessons learned are included in some projects as a mandatory task.
20-22 | Planning - Risk |  | 3 | 13
Regardless of how important we believe formal risk identification and mitigation sessions are they are included in some projects as mandatory.
23-27 | Planning - Schedule |  | 6 | 32
Review main component and benefits of a schedule. The project schedule should capture scope to be delivered when, by what resources and the estimated budgets.
28 - 33 | Planning - Cost |  | 7 | 43
Next to importance of project scope we must know the estimated cost of the project. Cost components are extensive from initial project costs to closeout. They include contract terms and conditions, specifications, drawings, consultants, subcontractors, material, labor, travel, escalation and much more.
34 | Planning - Training & Quality |  | 1 | 7
Review how to provide training if required in our project, it can cost more than we initially estimate. Let’s discuss what “quality” really means in projects. To call it simply paperwork it not conclusive.
35 | Planning - Safety |  | 2 | 8
Safety belongs to the safety officer. No, not so quick, it belongs to everyone on the project.
36 | Planning - Security & Enviroment |  | 1 | 6
Review of typical security concerns. Thefts and threats include physical harm, cyber breaches, software manipulations and many more. Review the basics of collecting, handling and shipping waste and discuss how to protect the environment at our project site.
37 | Planning - Startup, Commissioning, and Creating a Punch List |  | 1 | 6
I know it is at the end of the job, but we must know what our startup and commissioning entails during the planning phase of the project. The owner/client will give us their punch list. That is one approach but let’s review a better way to generating and addressing a punch-list.
38 | Planning - Transition to Operations & Closeout |  | 1 | 6
Review how to prepare for a typical transition from completion of the physical work to the owner/client operation employees control and use of the equipment or facility. Closeout reports and other common documents/tasks required for project closeout will be discussed.
|  | TOTAL | 50 | 245
*One minute of time per question is included in each section to answer the question